## DOCUMENT AMENDMENT
IBSCR2023003 Fraud Enhancement
Test Script
Ref. Number: |  | KFH/FSD/IBSCR2023003
Module: |  | KFH Online
Ref. Document: |  | [APPROVED] Business Requirement - SMS MCMC Announcement 01082023.pdf
Document Amendment:
Rev. No | Date Updated | Description Of Change | Updated By | Reviewed By | Approved By
|  |  | <Name, Dept> | <Name, Dept> | <Name, Dept>
1.0 | 2023-10-27 | Initial Release | Amir Hakim Mior Professional Services | Lizahwati Basirun Professional Services | Tan Lee Yong Project Manager

## SYSTEM TEST SEQUENCE
SYSTEM TEST SEQUENCE:
SYSTEM |  | KFH Online
MODULE |  | -
REF. DOCUMENT |  | [APPROVED] Business Requirement - SMS MCMC Announcement 01082023.pdf
ITEM | ACTION | TEST CASE | DESCRIPTION | TESTER | TEST STEP | TEST STATUS | TEST START DATE | TEST END DATE | NOTES
TS 1.1 | Own account transfer | TC 1.1.1 To test on SMS TAC for Own Account Transfer | To test on the detection of proposed SMS TAC for Own Account Transfer
|  | TC 1.1.2 To test on SMS Notification for Own Account Transfer | To test on the detection of proposed SMS Notification for Own Account Transfer
|  | TC 1.1.3 To test on SMS Notification for Beneficiary Notification | To test on the detection of proposed SMS Notification for Beneficiary Notification
TS 1.2 | 3rd Party Transfer | TC 1.2.1 To test on SMS TAC for Open 3rd Party Transfer | To test on the detection of proposed SMS TAC for Open 3rd Party Transfer
|  | TC 1.2.2 To test on SMS Notification for Open 3rd Party Transfer | To test on the detection of proposed SMS Notification for Open 3rd Party Transfer
|  | TC 1.2.3 To test on SMS TAC for Fav 3rd Party Transfer | To test on the detection of proposed SMS TAC for Fav 3rd Party Transfer
|  | TC 1.2.4 To test on SMS Notification for Fav 3rd Party Transfer | To test on the detection of proposed SMS Notification for Fav 3rd Party Transfer
|  | TC 1.2.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.2.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.2.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
|  | TC 1.2.8 To test on SMS Notification for Beneficiary Notification | To test on the detection of proposed SMS Notification for Beneficiary Notification
TS 1.3 | IBG | TC 1.3.1 To test on SMS TAC for Open IBG | To test on the detection of proposed SMS TAC for Open IBG
|  | TC 1.3.2 To test on SMS Notification for Open IBG | To test on the detection of proposed SMS Notification for Open IBG
|  | TC 1.3.3 To test on SMS TAC for Fav IBG Transfer | To test on the detection of proposed SMS TAC for Fav IBG Transfer
|  | TC 1.3.4 To test on SMS Notification for Fav IBG Transfer | To test on the detection of proposed SMS Notification for Fav IBG Transfer
|  | TC 1.3.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.3.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.3.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
|  | TC 1.3.8 To test on SMS Notification for Beneficiary Notification | To test on the detection of proposed SMS Notification for Beneficiary Notification
TS1.4 | DuitNow | TC 1.4.1 To test on SMS TAC for Open DuitNow | To test on the detection of proposed SMS TAC for Open DuitNow
|  | TC 1.4.2 To test on SMS Notification fo Open DuitNow | To test on the detection of proposed SMS Notification for Open DuitNow
|  | TC 1.4.3 To test on SMS TAC for Fav DuitNow | To test on the detection of proposed SMS TAC for Fav DuitNow
|  | TC 1.4.4 To test on SMS TAC for Fav DuitNow | To test on the detection of proposed SMS TAC for Fav DuitNow
|  | TC 1.4.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.4.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.4.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
TS1.5 | DuitNow ID - Maintenance | TC 1.5.1 To test on SMS TAC for DuitNow ID - Activation | To test on the detection of proposed SMS TAC for DuitNow ID - Activation
|  | TC 1.5.2 To test on SMS Notification for DuitNow ID - Activation | To test on the detection of proposed SMS Notification for DuitNow ID - Activation
|  | TC 1.5.3 To test on SMS TAC for DuitNow ID - Deactivation | To test on the detection of proposed SMS TAC for DuitNow ID - Deactivation
|  | TC 1.5.4 To test on SMS Notification for DuitNow ID - Deactivation | To test on the detection of proposed SMS Notification for DuitNow ID - Deactivation
|  | TC 1.5.5 To test on SMS TAC for DuitNow ID - Deregister | To test on the detection of proposed SMS TAC for DuitNow ID - Deregister
|  | TC 1.5.6 To test on SMS Notification for DuitNow ID - Deregister | To test on the detection of proposed SMS Notification for DuitNow ID - Deregister
|  | TC 1.5.7 To test on SMS TAC for DuitNow ID - Update Account No | To test on the detection of proposed SMS TAC for DuitNow ID - Update Account No
|  | TC 1.5.8 To test on SMS Notification for DuitNow ID - Update Account No | To test on the detection of proposed SMS Notification for DuitNow ID - Update Account No
|  | TC 1.5.9 To test on SMS TAC forDuitNow ID - Registration | To test on the detection of proposed SMS TAC for DuitNow ID - Registration
|  | TC 1.5.10 To test on SMS Notification for DuitNow ID - Registration | To test on the detection of proposed SMS Notification for DuitNow ID - Registration
TS1.6 | Foreign Telegraphic Transfer | TC 1.6.1 To test on SMS TAC for Open FTT | To test on the detection of proposed SMS TAC for Open FTT
|  | TC 1.6.2 To test on SMS Notification for Open FTT | To test on the detection of proposed SMS Notification for Open FTT
|  | TC 1.6.3 To test on SMS TAC for Registered FTT (1st time transaction) | To test on the detection of proposed SMS TAC for Registered FTT (1st time transaction)
|  | TC 1.6.4 To test on SMS Notification for Registered FTT (1st time transaction) | To test on the detection of proposed SMS Notification for Registered FTT (1st time transaction)
|  | TC 1.6.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.6.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.6.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
TS1.7 | Bill Payment | TC 1.7.1 To test on SMS TAC for Open Bill Payment | To test on the detection of proposed SMS TAC for Open Bill Payment
|  | TC 1.7.2 To test on SMS Notification for Open Bill Payment | To test on the detection of proposed SMS Notification for Open Bill Payment
|  | TC 1.7.3 To test on SMS TAC for Registered Bill Payment | To test on the detection of proposed SMS TAC for Registered Bill Payment
|  | TC 1.7.4 To test on SMS Notification for Registered Bill Payment | To test on the detection of proposed SMS Notification for Registered Bill Payment
|  | TC 1.7.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.7.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.7.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
TS1.8 | JOMPAY | TC 1.8.1 To test on SMS TAC for Open JOMPAY | To test on the detection of proposed SMS TAC for Open JOMPAY
|  | TC 1.8.2 To test on SMS Notification for Open JOMPAY | To test on the detection of proposed SMS Notification for Open JOMPAY
|  | TC 1.8.3 To test on SMS TAC for Registered JOMPAY | To test on the detection of proposed SMS TAC for Registered JOMPAY
|  | TC 1.8.4 To test on SMS Notification for Registered JOMPAY | To test on the detection of proposed SMS Notification for Registered JOMPAY
|  | TC 1.8.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.8.6To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.8.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
|  | TC 1.8.2 To test on SMS Notification for SI Unsuccessful Notification (new) | To test on the detection of proposed SMS Notification for SI Unsuccessful Notification (new)
TS1.9 | Prepaid Topup | TC 1.9.1 To test on SMS TAC for Prepaid Topup | To test on the detection of proposed SMS TAC for Prepaid Topup
|  | TC 1.9.2 To test on SMS Notification for Prepaid Topup | To test on the detection of proposed SMS Notification for Prepaid Topup
TS1.10 | Statutory Payment | TC 1.10.1 To test on SMS TAC for Open Statutory Payment | To test on the detection of proposed SMS TAC for Open Statutory Payment
|  | TC 1.10.2 To test on SMS Notification for Open Statutory Payment | To test on the detection of proposed SMS Notification for Open Statutory Payment
|  | TC 1.10.3 To test on SMS TAC for Registered Statutory Payment | To test on the detection of proposed SMS TAC for Registered Statutory Payment
|  | TC 1.10.4 To test on SMS Notification for Registered Statutory Payment | To test on the detection of proposed SMS Notification for Registered Statutory Payment
|  | TC 1.10.5 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.10.6 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.10.7 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
TS1.11 | Gold | TC 1.11.1 To test on SMS TAC for Open New Gold Account | To test on the detection of proposed SMS TAC for Open New Gold Account
|  | TC 1.11.2 To test on SMS Notification for Open New Gold Account | To test on the detection of proposed SMS Notification for Open New Gold Account
|  | TC 1.11.3 To test on SMS TAC for Buy Gold | To test on the detection of proposed SMS TAC for Buy Gold
|  | TC 1.11.4 To test on SMS Notification for Buy Gold | To test on the detection of proposed SMS Notification for Buy Gold
|  | TC 1.1.5 To test on SMS TAC for Sell Gold | To test on the detection of proposed SMS TAC for Sell Gold
|  | TC 1.11.6 To test on SMS Notification for Sell Gold | To test on the detection of proposed SMS Notification for Sell Gold
|  | TC 1.11.7 To test on SMS TAC for Open 3rd Party Gold Transfer | To test on the detection of proposed SMS TAC for Open 3rd Party Gold Transfer
|  | TC 1.11.8 To test on SMS Notification for Open 3rd Party Gold Transfer | To test on the detection of proposed SMS Notification for Open 3rd Party Gold Transfer
|  | TC 1.11.9 To test on SMS TAC for Registered Gold Transfer | To test on the detection of proposed SMS TAC for Registered Gold Transfer
|  | TC 1.11.10 To test on SMS Notification for Registered Gold Transfer | To test on the detection of proposed SMS Notification for Registered Gold Transfer
|  | TC 1.11.11 To test on SMS TAC for Add Favourite Beneficiary | To test on the detection of proposed SMS TAC for Add Favourite Beneficiary
|  | TC 1.11.12 To test on SMS TAC for Edit Favourite Beneficiary | To test on the detection of proposed SMS TAC for Edit Favourite Beneficiary
|  | TC 1.11.13 To test on SMS TAC for Delete Favourite Beneficiary | To test on the detection of proposed SMS TAC for Delete Favourite Beneficiary
|  | TC 1.11.14 To test on SMS Notification for Beneficiary Notification | To test on the detection of proposed SMS Notification for Beneficiary Notification
TS1.12 | FPX | TC 1.12.1 To test on SMS TAC for FPX | To test on the detection of proposed SMS TAC for FPX
|  | TC 1.12.2 To test on SMS Notification for FPX | To test on the detection of proposed SMS Notification for FPX
TS1.1.13 | Non-transactions | TC 1.13.1 To test on SMS TAC for Login from new device or browser | To test on the detection of proposed SMS TAC for Login from new device or browser
|  | TC 1.13.2 To test on SMS TAC for Concurrent Login | To test on the detection of proposed SMS TAC for Concurrent Login
|  | TC 1.13.3 To test on SMS TAC for Profile Maintenance | To test on the detection of proposed SMS TAC for Profile Maintenance
|  | TC 1.13.4 To test on SMS TAC for Change Password | To test on the detection of proposed SMS TAC for Change Password
|  | TC 1.13.5 To test on SMS Notification for Change Password | To test on the detection of proposed SMS Notification for Change Password
|  | TC 1.13.6 To test on SMS TAC for Change Security Answer | To test on the detection of proposed SMS TAC for Change Security Answer
|  | TC 1.13.7 To test on SMS Notification for Change Security Answer | To test on the detection of proposed SMS Notification for Change Security Answer
|  | TC 1.13.1 To test on SMS TAC for Activate KFH MySecure | To test on the detection of proposed SMS TAC for Activate KFH MySecure
|  | TC 1.13.2 To test on SMS TAC for Forget Password | To test on the detection of proposed SMS TAC for Forget Password
|  | TC 1.13.3 To test on SMS TAC for Forget Security Answer | To test on the detection of proposed SMS TAC for Forget Security Answer
|  | TC 1.13.3 To test on SMS TAC for Forget Password and Security Answer | To test on the detection of proposed SMS TAC for Forget Password and Security Answer
SYSTEM |  | IBG Engine
MODULE
REF. DOCUMENT |  | [APPROVED] Business Requirement - SMS MCMC Announcement 01082023.pdf
ITEM | ACTION | TEST CASE | DESCRIPTION | TESTER | TEST STEP | TEST STATUS | TEST START DATE | TEST END DATE | NOTES
TS 2.1 | IBG RFI Crediting | TC 1.13.2 To test on SMS TAC for IBG RFI Crediting | To test on the detection of proposed SMS TAC for IBG RFI Crediting
SYSTEM |  | CORUS
MODULE
REF. DOCUMENT |  | [APPROVED] Business Requirement - SMS MCMC Announcement 01082023.pdf
ITEM | ACTION | TEST CASE | DESCRIPTION | TESTER | TEST STEP | TEST STATUS | TEST START DATE | TEST END DATE | NOTES
TS 3.1 | First Time Login | TC 1.13.1 To test on SMS PIN for First Time Login | To test on the detection of proposed SMS PIN for First Time Login
TS 3.1 | Reset Password | TC 1.13.1 To test on SMS PIN for Reset Password | To test on the detection of proposed SMS PIN for First Time Login
TS 3.1 | Reset Secure Pass | TC 1.13.1 To test on SMS PIN for Reset Secure Pass | To test on the detection of proposed SMS PIN for Reset Secure Pass
Note on D105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kebarangkalian untuk test case and elaboration punya isi is sama lol
Note on D112: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kebarangkalian untuk test case and elaboration punya isi is sama lol
Note on D113: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dlm pdf takda contoh pin yang akan terpapar

## TS 1.1
TS 1.1 Login
TC 1.1.1 To test on login with same account but with different device
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail/NA | Remarks
TC 1.1.1.1 | To test with login with account (hatesting) for 1st time (laptop) Step 1: User enter KFH Online with a new device via laptop | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 1 step-up authentication |  | The user logout after login
Screenshot:
TC 1.1.1.2 | To test with same account (hatesting) but with different device (handphone) Step 1: User enter KFH Online with a new device via handphone | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1)System prompted TAC window and counted as 2 step-up authentication |  | The user logout after login
Screenshot:
TC 1.1.1.3 | To test with same account (hatesting) but with different device (tablet) Step 1: User enter KFH Online with a new device via tablet | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted popup message and block the account 2) User not able to login and need to call contact center
Screenshot:
TC 1.1.2 To test on login with same account but with different location
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail/NA | Remarks
TC 1.1.2.1 | To test with login with account (hatesting) for 1st time ( KL ) Step 1: User enter KFH Online with a new location in Kuala Lumpur | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 1 step-up authentication
Screenshot:
TC 1.1.2.2 | To test with login with account (hatesting) for 2nd time ( Johor ) Step 1: User enter KFH Online with a new location in Johor | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 2 step-up authentication
Screenshot:
TC 1.1.2.3 | To test with login with account (hatesting) for 3rd time ( Kedah ) Step 1: User enter KFH Online with a new location in Kedah | KFH Online > Login | 1. Enter username "hatesting" and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System counted as 3 step-up authentication 2) User not able to login and need to call contact center
Screenshot:
TC 1.1.3 To test on 3rd step up authenthication but with different single sign on (multiple login detected)
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail/NA | Remarks
TC 1.1.3.1 | To test with login with account (hatesting) for 1st time ( Google Chrome ) Step 1: User enter KFH Online with a new Google Chrome tab | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 1 step-up authentication
Screenshot:
TC 1.1.3.2 | To test with login with account (hatesting) for 2nd time ( Microsoft Edge ) Step 1: User enter KFH Online with a new Microsoft Edge tab | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 2 step-up authentication
Screenshot:
TC 1.1.3.3 | To test with login with account (hatesting) for 3rd time ( Safari ) Step 1: User enter KFH Online with a new Safari tab | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System counted as 3 step-up authentication 2) System prompted popup message and block the account 3) User not able to login and need to call contact center
Screenshot:
TC 1.1.4 To test on login with same account but with various fraud detection (new device, new location & multiple device)
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail/NA | Remarks
TC 1.1.4.1 | To test with login with account (hatesting) for 1st time ( laptop ) Step 1: User enter KFH Online with a new device via laptop | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 1 step-up authentication
Screenshot:
TC 1.1.4.2 | To test with login with account (hatesting) for 2nd time ( Johor ) Step 1: User proceed to enter KFH Online with the same laptop in a different location, Johor | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System prompted TAC window and counted as 2 step-up authentication
Screenshot:
TC 1.1.4.3 | To test with login with account (hatesting) for 2nd time ( Safari ) Step 1: User proceed to enter KFH Online with the same laptop in Johor but using a different browser, Safari. | KFH Online > Login | 1. Enter username and click on Login button 2. Tick on Security Phrase 3. Enter password and click on Next button | 1) System counted as 3 step-up authentication 2) System prompted popup message and block the account 3) User not able to login and need to call contact center
Screenshot:

## TS 1.2
TS 1.2 Transaction
TC 1.2.1 To test on transaction upward amount for same module Open 3rd Party Transfer
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 1.2.1.1 | To test Open 3rd party transfer with amount RM10 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open 3rd Party | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | User successfully perform open 3rd party transfer
Screenshot:
TC 1.2.1.2 | To test Open 3rd party transfer with amount RM11 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open 3rd Party | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System prompted security question and count as 1st step-up authentication
Screenshot:
TC 1.2.1.3 | To test Open 3rd party transfer with amount RM12 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open 3rd Party | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System prompted security question and count as 2nd step-up authentication
Screenshot:
TC 1.2.1.3 | To test Open 3rd party transfer with amount RM13 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open 3rd Party | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System prompted popup message and block the user
Screenshot:
TC 1.2.2 To test on transaction upward amount for different module Open 3rd Party Transfer & Open DuitNow
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 1.2.2.1 | To test Open 3rd party transfer with amount RM10 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open 3rd Party | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | User successfully perform open 3rd party transfer |  | Prerequisite user already have 2 step authentication
Screenshot:
TC 1.2.2.2 | To test Open DuitNow transfer with amount RM10 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open DuitNow Transfer | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | User successfully perform Open DuitNow transfer
Screenshot:
TC 1.2.2.3 | To test Open DuitNow transfer with amount RM11 Step 1: User does a transaction in KFH Online | KFH Online > Fund Transfer>Open DuitNow Transfer | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System will prompt popup error message and block the user. System logged out the user.
Screenshot:
TC 1.2.3 To test on total transaction amount for same module Open 3rd Party Transfer
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 1.2.3.1 | To test Open 3rd party transfer with amount RM47 Step 1: User does a transaction in KFH Online | KFH Online > Transaction | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System prompted security question and count as 1st step-up authentication |  | Prerequisite user has been locked and already unlocked the account. The step-up counter become "0". The total transaction amount for Open 3rd Party Transfer=RM46
Screenshot:
TC 1.2.3.1 | To test Open 3rd party transfer with amount RM48 Step 1: User does a transaction in KFH Online | KFH Online > Transaction | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System prompted security question and count as 2nd step-up authentication
Screenshot:
TC 1.2.3.1 | To test Open 3rd party transfer with amount RM49 Step 1: User does a transaction in KFH Online | KFH Online > Transaction | 1. Enters transaction module 2. Keys in transaction detail 3. Perform transaction | System will prompt popup error message and block the user. System logged out the user.
Screenshot:

## TS 2.1
TS 2.1 Fraud Frequency Parameter
TC 2.1.1 To view the number of step-up authentication attempt
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 2.1.1.1 | To view on the number of step-up authentication attempt Step 1: View the data of number of step-up authentication attempt | Corus>IB Login>Password Configuration Management | 1. User access Corus>IB Login>Password Configuration Management 2. View Step-up authentication attempt | System will display Password Configuration Management screen
Screenshot:
TC 2.1.2 To edit the number of step-up authentication attempt and to test the functionality
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 2.2.1.1 | To edit on the number of step-up authentication attempt Step 1: Edit the data of number of step-up authentication attempt | Corus>IB Login>Password Configuration Management | 1. User access Corus>IB Login>Password Configuration Management 2. Edit Step-up authentication attempt into 2 | System will change the step up authenthication from 3 into 2 |  | Prerequisite default value by system for Step-Up Authentication Attempt=3
Screenshot:
TC 2.2.2.1 | To test on the functionality of changed Step-up authentication parameter Step 2: Edit the data of number of step-up authentication attempt | Corus>IB Login>Password Configuration Management | 1. User access Corus>IB Login>Password Configuration Management 2. Edit Step-up authentication attempt into 2 | System will change the step up authenthication from 3 into 2 |  | Prerequisite default value by system for Step-Up Authentication Attempt=3
Screenshot:

## TS 3.1
TS 3.1 Suspected Fraud Unlock
TC 3.1.1 To To view suspected fraud locked account
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 3.1.1.1 | To view the locked suspected fraud user account Step 1: View the locked suspected fraud user account | BVMC > Users > Search | 1. User access BVMC 2. User search the locked user | System displayed the user details with status "Suspected Fraud Lock"
Screenshot:
TC 3.1.2 To unlock suspected fraud locked account
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 3.2.1.1 | To unlock the locked suspected fraud user account Step 1: Edit the customer details | BVMC > Users > Search>Edit | 1. User access BVMC 2. User search the locked user 3. Edit the user detail 4. Change "Account Status" to "Fraud Unlock" 5. Click on Save button | System displayed the user details with status "Lock Fraud Lock"
Screenshot:
TC 3.1.3 To Print/Save IB report
Case No. | Test Description | Action/Path | Test Step Details | Expected Result | Status Pass/Fail | Remarks
TC 3.2.1.1 | To print or save "Suspected Fraud Lock Report" Step 1: Fill in IB report criteria | BVMC > Users > IB Report | 1. User access BVMC 2. User Fill in IB report criteria 3. Print Or Save IB report | System displayed the details of the report browsed
Screenshot: