Implementation Checklist for MPI Revamp

# Information URS Number: NETMAN Change : CHG76002 TSK3 Implementation Date: 26 April 2014

Prepared By,

#### VINCENT DEVETHAS,

PENRIL DATABILITY

- PREPARATION: Pre-activity

| Step | Date | Time | # Activity | Responsibility | Status/ Remarks |
| --- | --- | --- | --- | --- | --- |
|  | 16/04/2014 |  | UAT Sign-Off | MPI Team |  |
|  | 17/04/2014 |  | Preparation of migration patch | Penril |  |
|  | 17/04/2014 |  | Preparation of database script & migration list | Penril |  |
|  | 25/04/2014 |  | Disable the CV Alerts of MPI’s ( send email to monitoring team ) | IT M2U/ Monitoring teams |  |
|  | 25/04/2014 |  | Get all the netman approval | IT M2U |  |
|  | 25/04/2014 |  | DBA to backup MPI table : - List of table need to be backup | DBA - Suhailan |  |
|  | 25/04/2014 |  | Backup for MSS new existing servers | Penril/IT M2U |  |

- PREPARATION: Pre-activity for servers

| Step | Date | Time | # Activity | Responsibility | Status/ Remarks |
| --- | --- | --- | --- | --- | --- |
|  | 25/04/2014 |  | For Servers 172.31.51.52 (Target to have for MPI old and MPI new ) - At webservers iplanet (172.31.50.34) - Disable connection to M2U Cambodia (ssl and ssl admin) - Disable connection to M2U PnG (ssl and ssl admin) - At Weblogic Console url :http://172.31.51.52:7003/console/login/LoginForm.jsp (Cambodia) - Stop the rib services - At Weblogic Console url :http://172.31.51.52:7005/console/login/LoginForm.jsp (PnG) - Stop the rib services For Servers 172.31.51.46 (target to have Cambodia and PnG only) - At webservers iplanet (172.31.50.33) - Disable connection to M2U Phillipines (ssl and ssl admin) - At Weblogic Console url: http://172.31.51.52:7001/console/login/LoginForm.jsp (Phillipines) - Stop the rib services | IT M2U |  |
|  | 25/04/2014 |  | Set the maintenance page for MPI at servers 172.31.51.52 from 0 am to 7.00 am - cd /opt/wlsun/maintpage/Philippines - vi maintpage.sh |  |  |

- Cutover Activity

| Step | Date Time | Duration | # Activity | Responsibility | Status/ Remarks |
| --- | --- | --- | --- | --- | --- |
|  | 26/04/2014 01:00-02:00 | 60 minutes | Table creation & Data migration - Run script to create new tables. - Data migration – Run script to insert *Refer to Appendix B for the steps & details of the DB scripts. | MBB IT |  |
|  | 26/04/2014 01:00-02:00 | 60 minutes | - Network Configuration - URL Routing at F5 - URL Configuration at Web Server | MBB IT |  |
|  | 26/04/2014 02:00-02:30 | 30 minutes | - Deployment of Resources to Web Server - Configuration at Web Server iPlanet | MBB IT & Penril |  |
|  | 26/04/2014 02:30-03:00 | 30 minutes | - Deployment of the MPI New version - Access application from App Server to make sure it’s up and running. - Access application from Web Server to make sure it accessible. *Refer to Appendix A for application deployment guide. | MBB IT & Penril |  |
|  | 26/04/2014 03:00-07:00 | 4 hours | Live test on both old and new version of MPI Checkpoint 1 at 0400 - Check the screen layout and display. - Check all the images are visible. - Check all the modules and navigation If problem due to navigation data / could not load the images / layout not display correctly, to rectify in 30 minutes. Checkpoint 2 at 0500 - Check Account Enquiries and transaction history - Check on Transaction module If problem due to host response / other issue, to rectify in 30 minutes. If problem required program change, conduct fallback. Escalate to respective Unit Head and Project Leader of the live test result. *Refer to Appendix A for fallback plan. Checkpoint 3 at 0600 - Check on Contact Us – Email receive If problem due to host response / other issue, to rectify in 30 minutes. If problem required program change, conduct fallback. Escalate to respective Unit Head and Project Leader of the live test result. *Refer to Appendix A for fallback plan. | MPI Team/MBB IT |  |

- Fallback Plan

No fallback activity. The cutover is on pilot version.

4. Standby List

|  | Date | Time | Role/ Area | Name | Mode of Standby | Location | Contact |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 01:00 | 06:00 | Technical/DCM2U | Dennis | On-site | 30th Floor | Ext: 3684 H/P: 019-2642285 |
|  | 01:00 | 07:00 | Technical/DCM2U | Suriati | Off-site | 30th Floor | Ext: 3684 H/P: 013-341 2680 |
|  | 01:00 | 07:00 | Technical/DCM2U | Tan Huilee | Off-site | 30th Floor | Ext: 4871 H/P: 012-3616197 |
|  | 01:00 | 07:00 | Project Director | Cheah Lu Hsun | On-site | 30th Floor | H/P:012-300 5411 |
|  | 01:00 | 07:00 | User Project Manager | Edgardo Christobal | Off-site | 30th Floor | H/P:+63 917 392 1686 |
|  | 01:00 | 07:00 | Tester | Corazon | Off-site | 30th Floor | H/P: |
|  | 01:00 | 07:00 | Tester | Jan Magallanes | Off-site | 30th Floor | H/P: |
|  | 01:00 | 07:00 | Tester | Maverick Galang | Off-site | 30th Floor | H/P: |
|  | 01:00 | 07:00 | Penril | Najmi | On-site | 30th Floor | H/P: 019-313 4405 |
|  | 01:00 | 07:00 | Penril | Ngoh Chee Ping | On-site | 30th Floor | H/P: 016-530 0206 |
|  | 01:00 | 07:00 |  |  |  |  |  |
|  | 01:00 | 07:00 |  |  |  |  |  |
|  | 01:00 | 07:00 |  |  |  |  |  |
|  | 01:00 | 07:00 |  |  |  |  |  |

- Appendix B

The complete step of application deployment is documented in a separate document. Please refer to the below attachment. The guide inclusive of fallback plan as well in case needed.

- Appendix A

| Step | # Activity |  |
| --- | --- | --- |
|  | Back up Database - Backup MPI Database instance. |  |
|  | Database Sever Copy deployment files - Login to Database Sever using FTP Client. - Go to directory /export/home/smn062. - Copy the below sql files from local machine to this directory. - create_mpi_revamp_tables.sql - insert_mpi_revamp_data.sql Create new tables - SSH to Production Database Server. - Execute the following command to login to MPI Production Database: sqlplus mpiibp/mpiibp@mpip. - Execute the SQL file to create new table by run this command: @/export/home/smn062/create_mpi_revamp_tables.sql Insert Data - Execute the SQL file to create new table by run this command: @/export/home/smn062/insert_mpi_revamp_data.sql - Once the above scripts executed, login to database (via database client) to verify whether the tables and data are in place. |  |