Document Name	: Agrobank CUA Migration Plan

Migration Plan ID	: ID01XX

Scheduled Date		: XX/10/2019

# Issue / Case ID

| Support Plus / Redmine ID | LANDesk | Description |
| --- | --- | --- |
| N/A |  | N/A Any Support Plus ID that is already gone into previous Internet Banking Current Production before above schedule date, will be included in CUA. |

# Check List

PROD

| No | # Item | Responsibility |
| --- | --- | --- |
|  | IBAPPSVR1 ready, WAS Admin username and password ready | Agrobank |
|  | IBAPPSVR2 ready, WAS Admin username and password ready | Agrobank |
|  | IBSQLSVR1 ready, DBA username and password ready | Agrobank |
|  | IBSQLSVR2 ready, DBA username and password ready | Agrobank |

DR

| No | # Item | Responsibility |
| --- | --- | --- |
|  | IBAPPSVR1DR ready, WAS Admin username and password ready | Agrobank |
|  | IBSQLSVR1DR ready, DBA username and password ready | Agrobank |

Related setup checklist

| No | # Item | Modification |
| --- | --- | --- |
|  | IBAM settings | No |
|  | Database | Yes |
|  | Websphere JNDI Setting for CUA DB | Yes, New |
|  | Websphere JDBC Connection Setting for CUA DB | No, Default |
|  | Config files deployment | Yes |
|  | ESB | Yes |
|  | Web Server (SMS) | No |
|  | IBM WAS plugin setup | No |
|  | IBM HTTP Server | No |

Server IP

| Server | IP |
| --- | --- |
| IBAPPSVR1 | 172.16.51.23 |
| IBAPPSVR2 | 172.16.51.24 |
| IBAPPSVR1DR | 172.16.54.22 |
| IBSQLSVR1 | 172.16.51.28 |
| IBSQLSVR2 | 172.16.51.29 |
| IBAPPSVR1DR | 172.16.54.22 |
| IBSQLSVR1DR | 172.16.54.25 |
| IBWEBSVR1 | 172.16.50.21 |
| IBWEBSVR2 | 172.16.50.22 |
| IBWEBSVR1DR | 172.16.53.21 |
| IBGLASSFISH | 10.1.1.69 |
| IBGLASSFISHDR | N/A |
| IBOPGWEBSVR | 172.16.50.28 |
| IBOPGWEBSVRDR | N/A |
| VPIBKW01 | 172.16.50.30 |
| VPIBKW02 | 172.16.50.31 |
| VPIBKA01 | 172.16.51.48 |
| VPIBKA02 | 172.16.51.49 |
| VPIBKU01 | 172.16.51.50 |
| VPIBKU02 | 172.16.51.51 |
| VRIBKW01 | 172.16.54.45 |
| VRIBKA01 | 172.16.54.46 |
| VRIBKU01 | 172.16.54.47 |

Project to Deploy

| Project | Migration # |
| --- | --- |
| Provide newest IBAM war file |  |
| Provide newest RIB war file |  |
| Provide newest BIB war file |  |
| Provide new CUA RESTful file |  |
| Provide new API Gateway RESTful file |  |
| Provide newest UPASS SOAP Web Service |  |

# Implementation Plan

| # Activity |  |  |
| --- | --- | --- |
| 1. |  | Update configuration |
| IBAM - Copy below file into “..\agro-admin.war\WEB-INF \” - web.xml* - Copy below file into “..\agro-admin.war\WEB-INF\classes\com\ib\hibernate\configuration\” - hibernate.cfg.xml* - Copy below file into “..\agro-admin.war\WEB-INF\classes\” - log4j.xml* - Copy below file into “..\agro-admin.war\template\” - header_css.jsp* * Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\IBAM * Please note that hibernate.cfg.xml for GlassFish deployment is different with WebSphere |  |  |
| RIB - Copy below file into “..\agro-rib.war\WEB-INF \” - web.xml* - Copy below file into “..\agro-rib.war\WEB-INF\classes\com\ib\hibernate\configuration\” - hibernate.cfg.xml* - Copy below file into “..\agro-rib.war\WEB-INF\classes\” - log4j.xml* - Copy below file into “..\agro-rib.war\layout \”. - footer.jsp* *Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\RIB |  |  |
| BIB - Copy below file into “..\agro-bib.war\WEB-INF \”. - web.xml* - Copy below file into “..\agro-bib.war\WEB-INF\classes\com\ib\hibernate\configuration\”. - hibernate.cfg.xml* - Copy below file into “..\agro-bib.war\WEB-INF\classes\”. - log4j.xml* - Copy below file into “..\agro-bib.war\layout \”. - footer.jsp* *Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\BIB |  |  |
| API GATE WAY - Copy below file into “..\agro-api-gate-way.war\WEB-INF \”. - web.xml* - Copy below file into “..\agro-api-gate-way.war\WEB-INF\classes\com\ib\hibernate\configuration\”. - hibernate.cfg.xml* - Copy below file into “..\agro-api-gate-way.war\WEB-INF\classes\”. - log4j.xml* *Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\API GATE WAY |  |  |
| CUA RESTFUL - Copy below file into “..\agro-api-gate-way.war\WEB-INF \”. - web.xml* - Copy below file into “..\agro-api-gate-way.war\WEB-INF\classes\com\ib\hibernate\configuration\”. - hibernate.cfg.xml* - Copy below file into “..\agro-api-gate-way.war\WEB-INF\classes\”. - log4j.xml* *Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\API GATE WAY |  |  |
| UPASS WS - Copy below file into “..\agro-cua-upass-ws.war\WEB-INF \”. - web.xml* - Copy below file into “..\agro-cua-upass-ws.war\WEB-INF\classes\com\ib\hibernate\configuration\”. - hibernate.cfg.xml* - Copy below file into “..\agro-cua-upass-ws.war\WEB-INF\classes\”. - log4j.xml* *Files are provided in Development Server (172.16.49.2) Path: D:\configuration\Production\UPASS WS |  |  |
| 2. | Check all URL in wsdl (IBAM, RIB and BIB lib > agro-esb-0.7-SNAPSHOT.jar) |  |
| - AgroBankEPAY.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:8080/ AgroBankESBProject/ebws/EPAYService/EPAYReload"/> - AgroBankArRahnu.wsdl <soap:address location="http://middleware:8080/ArRahnu/MicrolinkServices" /> - AgroBankBulk.wsdl <soap:address location='http://fusehaprod.agrobank.bpmb.local:8080/OnlineServices/BFT/JobServices'/> - AgroBankEIBFTAccountInquiry.wsdl <soap:address location="http://middleware:8080/OnlineServices/CB/AccountInquiryServices"/> - AgroBankEIBFTMonetary.wsdl <soap:address location="http://middleware:8080/OnlineServices/CB/MonetaryServices"/> - AgroBankMandateService.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:8080/OnlineServices/PAYMENZ/MandateServices"/> - AgroBankNBPS.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:8080/OnlineServices/MYC/PaymentServices"/> - RPPAccountServices.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:9000/cxf/RPPAccountServices"/> - RPPGetBankList.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:9000/cxf/GetBankListServices"/> - RPPGetMobileList.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:9000/cxf/GetMobileListServices" /> - RPPNADServices.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:9000/cxf/NADServices"/> - RPPProxyServices.wsdl <soap:address location="http:// fusehaprod.agrobank.bpmb.local:9000/cxf/ProxyServices"/> - RPPTransactionPosting.wsdl <soap:address location="http://fusehaprod.agrobank.bpmb.local:9000/cxf/TransPostingServices"/> |  |  |
| 3. | Run Script |  |
| - Please back up affected table before run all provided sql script From the link given is the step to backup affected table Link: https://www.mssqltips.com/sqlservertip/4822/exploring-sql-server-table-backup-methods/ Affected table: 1. TB_AM_APPSERV 2. TB_AM_CHANNEL 3. TB_AM_CONFIG 4. TB_AM_GROUP 5. TB_AM_LICENSE 6. TB_AM_PAIRING 7. TB_AM_PASSWORD 8. TB_AM_POLICY 9. TB_AM_SESSION 10. TB_AM_TAC 11. TB_AM_UPASS_ACTIVITY 12. TB_AM_USER 13. TB_AM_USER_CHANNEL 14. TB_AM_VASCO 15. TB_MK_TRNX_MASTER 16. TB_QR_LOGIN_Q 17. FTOTP_ADMIN_GROUP 18. FTOTP_ADMIN_LOG 19. FTOTP_ADMIN_ROLE 20. FTOTP_ADMIN_USER 21. FTOTP_AGENT_HOST 22. FTOTP_AGENTINFO 23. FTOTP_CONFIGINFO 24. FTOTP_DOMAININFO 25. FTOTP_GROUP 26. FTOTP_HOSTINFO 27. FTOTP_LICINFO 28. FTOTP_LOGINFO 29. FTOTP_TOKENEXT 30. FTOTP_TOKENINFO 31. FTOTP_TUSER 32.FTOTP_USER_GROUP 33. FTOTP_USER_TOKEN 34. FTOTP_USERINFO 35. FTOTP_ZONEINFO - Run below script in sequence; - Run 1 - CREATE AND INSERT.sql - Run 2 - CLEAN UP TABLE.sql - Run migrarionTool.jar on cmd - Run 1 - MIGRATE FTOTP TABLE AND DATA FROM PROD IB TO PROD CUA.sql - Run 2 - ADD UPASSADMIN IBAM, RIB, BIB.sql - Run 3 - DROP TABLE.sql |  |  |
| 4. | Update AppConfig |  |
| IBAM 1. Backup IBAMAppConfig 2. Find this value below: application.upass.admin.id=UpassAdmin application.upass.admin.password=UpassAdmin 3. Overwrite with value below: application.upass.admin.id=UpassAdminIBAM application.upass.admin.password=UpassAdmin application.upass.admin.rib.id=UpassAdminRIB application.upass.admin.rib.password=UpassAdmin application.upass.admin.bib.id=UpassAdminBIB application.upass.admin.bib.password=UpassAdmin |  |  |
| API GATE WAY 1. Make a clone from RIBAppConfig rename with MRIBAppConfig 2. Add below: #UpassRestClient upass.rest.client.url=http://[CUA RESTFUL PROD URL] |  |  |

Migration Drill

Penril suggested to perform “migration drill” as a part of Pre-Deployment Plan. Because CUA enhancement is considered as a high risk activity, since it requires Customer Authentication data migration. Failed during migration will cause user not able to perform login.

Therefore, with migration drill plan, it is expected that below factors are calculated and tested properly in production environment:

      - Successful backup on the existing WAR files,

      - Successful backup on the existing Internet Banking Database,

        - We need to identify the exact duration taken of backing up the IB database

      - Successful CUA database creation,

        - Although this has been tested successfully in UAT, we need to familiarize with tech refresh environment in production.

      - Successful Customer Authentication Data migration from IB to CUA DB,

        - To ensure that data can be migrated properly from IB to CUA using runnable jar program. This runnable java program must run using JDK 1.8,

      - Successful certain table drop at IB Database

        - Upon successful data migration from IB to CUA database, several original tables will be dropped from IB.

Activities of Migration Drill (Day 1)

| Time | # Duration | # Activity | Responsibility |
| --- | --- | --- | --- |
| 12:00am | 6 hours | To perform all migration activities mentioned in next table | Agrobank/Penril |
|  | 10 min | Update all VM IP Address for Production/DR | Agrobank/Penril |
|  | 10 min | Update hosts file in each VM accordingly | Agrobank/Penril |
|  | 10 min | Perform connection testing for each server | Agrobank/Penril |
|  | 10 min | Copy IBAM,RIB,BIB,upass war file from current Production App Server to tech refresh application server/authentication server | Agrobank/Penril |
|  | 10 min | Configure JNDI for Production DB & test connection | Agrobank/Penril |

Activities Before Cutover (Day 2)

| Time | # Duration | # Activity | Responsibility |
| --- | --- | --- | --- |
| 12:00am | 5 min | At App1, stop WAS services to bring down IBAM,RIB,BIB At App2, stop WAS services to bring down IBAM,RIB,BIB At App1 DR, stop WAS services to bring down IBAM,RIB,BIB At GLASSFISH server, stop IBAM application At Auth1, stop WAS services to bring down UPASS At Auth2, stop WAS services to bring down UPASS At Auth1 DR, stop WAS services to bring down UPASS | Agrobank/Penril |
| 12:05am | 5 min | At Development 172.16.49.2server | Agrobank/Penril |
|  |  | Backup IBAM WAR File Backup IBAM in “D:\was-workspace\agro-admin\” for current WAR file agro-admin.war to the “D:\was-workspace\ agro-admin \backup” location as a backup for IBAPPSVR1 and IBAPPSVR2 Backup RIB WAR File Backup RIB in “D:\was-workspace\agro-rib\” for current WAR file agro-rib.war to the “D:\was-workspace\ agro-rib\backup” location as a backup for IBAPPSVR1 and IBAPPSVR2 Backup BIB WAR File Backup BIB in “D:\was-workspace\agro-bib\” for current WAR file agro-bib.war to the “D:\was-workspace\ agro-bib\backup” location as a backup for IBAPPSVR1 and IBAPPSVR2 Backup Upass WAR File Backup Upass in “D:\was-workspace\authentication\” for current WAR file upass.war to the “D:\was-workspace\authentication\backup” location as a backuo for IBAUTSVR1 and IBAUTSVR2 |  |

Total Duration Taken: 10 min

Deployment

| Step | Time | Duration | # Activity | Remark |
| --- | --- | --- | --- | --- |
| 1. | Deploy application for IBAM/RIB/BIB/UPASS |  |  |  |
| 1.1 | 12:10am | 10 min | At VPIBKA01 (App Server 1) - Re-deploy IBAM War file provided in *“D:\was-workspace\agro-admin\agro-admin.war” | * path at Dev server (172.16.49.2) |
| 1.2 | 12:20am | 10 min | At VPIBKA02 (App Server 2) - Re-deploy IBAM War file provided in *“D:\was-workspace\agro-admin\agro-admin.war” |  |
| 1.3 | 12:30am | 10 min | At VRIBKA01 (App Server 1 DR) - Re-deploy IBAM War file provided in *“D:\was-workspace\agro-admin\agro-admin.war” |  |
| 1.4 | 12:40am | 10 min | At GLASSFISHSVR (App Server) Re-deploy IBAM War file provided in *“D:\was-workspace\agro-admin\agro-admin.war” |  |
| 1.5 | 12:50am | 10 min | At VPIBKA01 (App Server 1) - Re-deploy RIB War file provided in *“D:\was-workspace\agro-rib\agro-rib.war” | * path at Dev server (172.16.49.2) |
| 1.6 | 1:00am | 10 min | At VPIBKA02 (App Server 2) - Re-deploy RIB War file provided in *“D:\was-workspace\agro-rib\agro-rib.war” |  |
| 1.7 | 1:10am | 10 min | At VRIBKA01 (App Server 1 DR) - Re-deploy RIB War file provided in *“D:\was-workspace\agro-rib\agro-rib.war” |  |
| 1.8 | 1:20am | 10 min | At VPIBKA01 (App Server 1) - Re-deploy BIB War file provided in *“D:\was-workspace\agro-bib\agro-bib.war” | * path at Dev server (172.16.49.2) |
| 1.9 | 1:30am | 10 min | At VPIBKA02 (App Server 2) - Re-deploy BIB War file provided in *“D:\was-workspace\agro-bib\agro-bib.war” |  |
| 1.10 | 1:40am | 10 min | At VRIBKA01 (App Server 1 DR) - Re-deploy BIB War file provided in *“D:\was-workspace\agro-bib\agro-bib.war” |  |
| 1.11 | 1:50am | 10 min | At VPIBKU01 (Auth Server 1) Re-deploy Upass War file provided in *“D:\was-workspace\authentication\upass.war” |  |
| 1.12 | 2:00am | 10 min | At VPIBKU02 (Auth Server 2) Re-deploy Upass War file provided in *“D:\was-workspace\authentication\upass.war |  |
| 1.13 | 2:10am | 10 min | At VRIBKU01 (Auth Server 1 DR) Re-deploy Upass War file provided in *“D:\was-workspace\authentication\upass.war |  |
| 2 | Application Comfort Test |  |  |  |
| 2.1 | *Depends on Tester (compulsory to test every link) |  | 1. Clear cache at Internet Browser 2. Open this site in browser: IBAM: - http://vpibka01:9080/ibam - http:// vpibka02:9080/ibam - http:// vribka02:9080/ibam BIB: - http:// vpibka01:9081bib - http:// vpibka01:9082/bib - http:// vpibka02:9081/bib - http:// vpibka02:9082/bib - http:// vribka01:9081/bib RIB: - http:// vpibka01:9083/rib - http:// vpibka01:9084/rib - http:// vpibka02:9083/rib - http:// vpibka02:9084/rib - http:// vribka01:9083/rib UPASS - http:// vpibku01:9080/agro -upass-ws/services/WS_UPass?wsdl - http:// vpibku02:9080/agro -upass-ws/services/WS_UPass?wsdl - http:// vribku01:9080/agro -upass-ws/services/WS_UPass?wsdl |  |
|  |  |  | Check Point 2: Decide to proceed or fall back. If proceed, open to public If fall back, go to fall back plan | To call for decision to Fall back (if necessary) |

Total Duration Taken: 100 min

Fallback Plan

| Duration | # Activity | Responsibility |
| --- | --- | --- |
| 15 min | At IBAPPSVR1 (App Server 1) - Run WAS Service at IBAPPSVR1. | Penril/Agrobank |
| 15 min | At IBAPPSVR2 (App Server 2) - Run WAS Service at IBAPPSVR2. | Penril/Agrobank |
| 15 min | At IBAPPSVR1DR (App Server 1 DR) - Run WAS Service at IBAPPSVR1DR. | Penril/Agrobank |
| 15 min | At IBAUTHSVR1 (Auth Server 1) - Run WAS Service at IBAUTHVR1. | Penril/Agrobank |
| 15 min | At IBAUTHSVR2 (Auth Server 2) Run WAS Service at IBAUTHVR2. | Penril/Agrobank |
| 15 min | At IBAUTHSVR1DR (Auth Server) Run WAS Service at IBAUTHVR2DR. | Penril/Agrobank |

Total Duration Taken: 60min

Estimated Total Duration Taken

| Details | Time Taken (min) |
| --- | --- |
| Backup | 10 |
| Implementation Plan | 100 |
| Fallback Plan | 90 |
| Total Duration Taken | 170 |

# Standby List

Standby Period: 10:00pm - 04:00am

Technical Support

| Name | Contact | Responsibility Area | Standby Mode | Location |
| --- | --- | --- | --- | --- |
| Norazlilah Binti Khamdan | 014-8133959 | Application | Offsite | - |

User Support

| Name | Contact | Responsibility Area | Standby Mode | Location |
| --- | --- | --- | --- | --- |
| Nora Ahmad | 012-2190920 | Project Manager | Offsite | - |

Vendor Support

| Name | Contact | Responsibility Area | Standby Mode | Location |
| --- | --- | --- | --- | --- |
| Bram | 011-2663-8339 | Application | Onsite | AgroBank HQ |
| Gabbytian | 018-294-7627 | Application | Onsite | AgroBank HQ |
| Stephanie | 016-620-4064 | Application | Onsite | AgroBank HQ |
| Balqis | 011-1025-1907 | Application | Onsite | AgroBank HQ |
| Lim Chun Feng | 012-9263163 | Server Infra | Onsite | AgroBank HQ |
| Ngoh Chee Ping | 016-5300-206 | Application | Offsite | Offsite |